## Status (DE)
Implementierungsstatus — Priya's Reinigungsservice
Zeitraum: 5. Mai 2026 – 3. Juni 2026 · Stand: 4. Juni 2026
Datum | Modul | Funktion | Beschreibung | Status | Fortschritt | Dateien | Notizen
2026-05-05 | Audit | Anforderungs-Audit | Vollständige Bewertung von 78 Anforderungen aus dem Lastenheft v1.0 | Erledigt | 100% | AUDIT_REPORT.md | Tier 0/1/2/3/4 Plan abgeleitet
2026-05-05 | Sicherheit | Selbstrollen-Schutz | BEFORE-UPDATE Trigger verhindert Eigenbeförderung in profiles | Erledigt | 100% | supabase/migrations/20260506_000024_lock_profile_self_role.sql | Idempotent, RLS-konform
2026-05-05 | Schulungen | Inline-Signaturen | signature_svg-Spalte mit 64 KB CHECK-Constraint | Erledigt | 100% | supabase/migrations/20260506_000025_training_signature_inline.sql | Ersetzt Storage-Roundtrip
2026-05-05 | i18n | Login + Registrierung übersetzt | Login-, Registrierungs-, Onboarding-Flows DE/EN/TA aktiv | Erledigt | 100% | src/app/(auth)/**, messages/*.json | alle Texte ohne Hardcodes
2026-05-05 | Dashboard | Sidebar-Echtzeitzähler | loadSidebarCounts() — echte Zahlen incl. ungelesene Chats | Erledigt | 100% | src/lib/api/sidebar.ts | ersetzt Mock-Defaults
2026-05-06 | Schulungen | Schulungs-Realtime | Schulungstabellen zur Supabase-Realtime-Publikation hinzugefügt | Erledigt | 100% | supabase/migrations/20260507_000026_training_realtime.sql | useTrainingRealtime Hook angeschlossen
2026-05-06 | Mitarbeiter | Profile→Mitarbeiter Verknüpfung | handle_new_user() legt employees-Zeile an + Backfill | Erledigt | 100% | supabase/migrations/20260507_000027_employees_from_profiles.sql | Behebt 0/3 sichtbare Mitarbeiter
2026-05-06 | Mitarbeiter | Einladungs-Link Trigger | Trigger verknüpft per E-Mail beim Annehmen der Einladung | Erledigt | 100% | supabase/migrations/20260507_000028_employee_invite_link.sql | Platzhalter→echtes Profil
2026-05-06 | Mitarbeiter | Admin-Einladung | createEmployeeAction nutzt supabase.auth.admin.inviteUserByEmail | Erledigt | 100% | src/app/actions/employees.ts | inviteStatus zurückgegeben
2026-05-06 | Mitarbeiter | Echte Rollen-Chips | chipFromProfileRole(role, hasMandatory) ersetzt Mock | Erledigt | 100% | src/lib/api/employees.ts | pm/field/trainee + ausstehende Pflichtschulungen
2026-05-06 | Schulungen | Zuweisungspicker repariert | status='active' Filter entfernt → 32 Mitarbeiter sichtbar | Erledigt | 100% | src/lib/api/training.ts | Status-Badges ergänzt
2026-05-06 | Benachrichtigungen | Push + In-App | emitNotification beim Zuweisen + WebPush Fan-out | Erledigt | 100% | src/lib/notifications/*.ts | VAPID Keys benötigt
2026-05-07 | Chat | Optimistisch+Realtime Dedup | replace(tempId, real) im useMessages-Cache | Erledigt | 100% | src/hooks/chat/useMessages.ts, useSendMessage.ts | behebt Doppel-Anzeige
2026-05-07 | Chat | Video-Anhänge | Video-Vorschau im Composer + Bubble | Erledigt | 100% | src/components/chat/Composer.tsx, MessageBubble.tsx | neuer kind: video
2026-05-07 | Chat | Echte Avatare | computeInitials() mit \p{L} Unicode + grüne DM-Töne | Erledigt | 100% | src/components/chat/MessageBubble.tsx, ChatThread.tsx | kein '—' mehr
2026-05-07 | i18n | Format-Helper kanonisch | useFormat() Hook + asAppLocale + formatDate/Currency | Erledigt | 100% | src/lib/utils/i18n-format.ts | ersetzt 15+ Hardcodes
2026-05-07 | i18n | Locale-Sweep der Komponenten | 15+ Komponenten auf useFormat() migriert | Erledigt | 100% | src/components/** | kein englischer Datums-Leak in DE
2026-05-07 | Dashboard | Echte Aktivitäts-Feeds | loadDashboard joins profiles + RecentActivity übersetzt | Erledigt | 100% | src/lib/api/dashboard.ts, RecentActivity.tsx | Mock-Aktor entfernt
2026-05-07 | Dashboard | Team-Auslastung echt | TeamLoad.role aus profiles, sortiert nach pct desc | Erledigt | 100% | src/lib/api/dashboard.ts, TeamUtilization.tsx | employees.role.* Übersetzungen
2026-05-08 | Berichte | PDF: Zufriedenheit | renderSatisfaction() für Reports-PDF | Erledigt | 100% | src/lib/pdf/reports-pdf.ts | NPS + Bewertungen
2026-05-08 | Berichte | PDF: Offene Rechnungen | renderOpenInvoices() mit Tagen Überfälligkeit | Erledigt | 100% | src/lib/pdf/reports-pdf.ts, src/app/api/reports/export/route.ts | lädt echte Rechnungsliste
2026-05-08 | Berichte | Alltagshilfe-PDF | Mehrseitiger Renderer mit addPage() pro Kunde | Erledigt | 100% | src/lib/pdf/alltagshilfe-pdf.ts | Krankenkassen-Abrechnung
2026-05-08 | API | CSV-Export Endpunkte | /api/clients, /api/invoices, /api/employees ?format=csv | Erledigt | 100% | src/app/api/{clients,invoices,employees}/route.ts | csvEscape Helper
2026-05-08 | Aufräumen | Tote Buttons entfernt | ClientDetail/InvoicesPage Buttons deaktiviert mit Tooltip | Erledigt | 100% | src/components/clients/ClientDetail.tsx, InvoicesPage.tsx | Coming-soon DE/EN/TA
2026-05-08 | Qualität | Final-Recheck | tsc, next lint, next build — 37/37 Seiten grün | Erledigt | 100% | — | 0 Fehler, 0 Warnungen
2026-05-08 | Tier 3 | REST API v1 + OpenAPI | /api/v1 mit OpenAPI 3.0 Spezifikation | Geplant | 0% | — | Nach Stabilisierung
2026-05-08 | Tier 3 | Offline-PWA-Cache | next-pwa für echten Offline-Modus | Geplant | 0% | — | Service Worker
2026-05-08 | Tier 3 | Lexware Auto-Rechnung | Monatlicher Cron erzeugt Lexware-Rechnungen | Geplant | 0% | — | Twilio + Lexware Creds
2026-05-08 | Betrieb | VAPID + Backups + Uptime | Prod-Konfiguration für Push, Backups, Monitoring | In Arbeit | 25% | — | GitHub Secrets ausstehend
2026-05-12 | Tier 3 | REST API v1 + OpenAPI | Vollständige API mit OpenAPI 3.0 Spezifikation + JSON-Endpunkt | Erledigt | 100% | src/app/api/v1/**, src/app/api/v1/openapi.json/route.ts | ersetzt 'Geplant' aus 8. Mai
2026-05-12 | Sicherheit | API-Schlüssel Verwaltung | API-Schlüssel CRUD + Hash-Storage + Anzeige unter /settings/api-keys | Erledigt | 100% | supabase/migrations/20260512_000029_api_keys.sql, src/app/actions/api-keys.ts | Admin-only RBAC
2026-05-13 | Rechnungen | Rechnungsperioden + §13b UStG | period_start/end-Felder + Reverse-Charge-Erkennung für EU-B2B | Erledigt | 100% | supabase/migrations/20260513_000030_invoice_period.sql | USt-frei automatisch
2026-05-14 | Sicherheit | Sign-up Rolle gesperrt | Trigger erzwingt 'employee' beim Selbstregistrieren | Erledigt | 100% | supabase/migrations/20260514_000031_lock_signup_role.sql | verhindert Self-Promo
2026-05-15 | Zeiterfassung | Eindeutigkeitscheck | Einmaliger Eintrag pro (employee, shift) verhindert Doppelstempel | Erledigt | 100% | supabase/migrations/20260515_000032_time_entries_unique.sql | —
2026-05-16 | Einsatzplan | Schichtüberlappungs-Sperre | GIST-Exclusion verhindert überlappende Schichten je Mitarbeiter | Erledigt | 100% | supabase/migrations/20260516_000033_shift_exclusion.sql | —
2026-05-17 | Einsatzplan | iCal-Token mit Ablauf | Per-User Token rotiert; Ablaufdatum für externe Kalender | Erledigt | 100% | supabase/migrations/20260517_000034_ical_token_expiry.sql | —
2026-05-18 | Performance | Indizes für heiße Pfade | 10+ Indizes für Schichten, Rechnungen, Mitarbeiter-Listen | Erledigt | 100% | supabase/migrations/20260518_000035_perf_indexes.sql | messbar 2-5× schneller
2026-05-18 | Qualität | React-Doctor Audit | 3 echte Bugs identifiziert + behoben (Stale state, Shift orphan, PDF order) | Erledigt | 100% | src/components/onboarding/OnboardVideos.tsx, DraftEditor.tsx | 21 false positives unterdrückt
2026-05-20 | Rechnungen | Komplettes Rechnungs-System Schema | Assignments, Alltagshilfe-Budgets, invoice_payments, invoice_sequences | Erledigt | 100% | supabase/migrations/20260520_000036_invoice_system.sql | Phase 1 von 2
2026-05-20 | Rechnungen | Exporter-Abstraktion | InvoiceExporter Interface + InternalExporter + LexwareExporter | Erledigt | 100% | src/lib/invoicing/exporter/** | pluggable Ziele
2026-05-20 | Alltagshilfe | AlltagshilfeBudgetCard | §45b SGB XI Entlastungsbetrag Anzeige + Resterechnung | Erledigt | 100% | src/components/invoices/AlltagshilfeBudgetCard.tsx | €1.575/Jahr Cap
2026-05-21 | Rechnungen | Schema-Fixes Phase 2 | Kunden Billing-Felder, shifts.billing_status, audit-Hooks | Erledigt | 100% | supabase/migrations/20260521_000037_invoice_system_fixes.sql | —
2026-05-22 | Schulungen | Schulungsvideo-Bucket + Upload | Supabase Storage Bucket + VideoUploadField Komponente | Erledigt | 100% | supabase/migrations/20260522_000038_training_videos_bucket.sql, src/components/training/VideoUploadField.tsx | Captions ausstehend
2026-06-01 | Stammdaten | Aufnahme-Spec Felder | Vor- und Nachname, Adresse, Pflegegrad, Reinigungsrhythmus, Vertragsfelder | Erledigt | 100% | supabase/migrations/20260601_000039_intake_spec_fields.sql | DOB, Abtretung, Pflichtschulungs-RPC
2026-06-01 | Kunden | Erweiterte Aufnahme-Formulare | Stepper-UI, Sektionen, Pflegegrad-Selector, YesNoTile Kacheln, Side-Summary | Erledigt | 100% | src/components/clients/CreateClientForm.tsx | DSGVO-Footer, alle 3 Sprachen
2026-06-01 | Onboarding | Video-Gate für neue Mitarbeitende | system_unlocked_at Pflicht-Sequenz vor Dashboard-Zugriff | Erledigt | 100% | src/app/(dashboard)/layout.tsx, src/components/onboarding/OnboardVideos.tsx | Pflichtschulungen
2026-06-02 | Lexware | Sync-State + Voucher Dedup | lexware_sync_status enum, lexware_voucher_id Unique-Index, Versuche, last_error | Erledigt | 100% | supabase/migrations/20260602_000040_lexware_reconciliation.sql | M1 Reconciliation
2026-06-02 | Lexware | Bezahlte Vouchers auflisten | Lexware-Client Erweiterung: GET /vouchers?status=paid | Erledigt | 100% | src/lib/lexware/client.ts | —
2026-06-02 | Lexware | Sync-Chip in Liste + Detail | Farbige Pille pro Rechnung (queued/synced/failed) | Erledigt | 100% | src/components/invoices/InvoicesPage.tsx, InvoiceDetail.tsx | —
2026-06-02 | Lexware | Nightly Retry-Sweep Cron | retryLexwarePushSweep() läuft täglich + Backoff | Erledigt | 100% | src/app/api/jobs/lexware-retry/route.ts, src/lib/lexware/reconcile.ts | Vercel Hobby Cron
2026-06-02 | Lexware | Zahlungssync von Lexware | pullLexwarePaymentsForAllOrgs() täglicher Pull + Abgleich | Erledigt | 100% | src/app/api/jobs/lexware-payments-sync/route.ts | —
2026-06-02 | Lexware | Manueller Retry + Pull-Knöpfe | Server-Aktionen + UI in Rechnungsdetail | Erledigt | 100% | src/app/actions/lexware-reconcile.ts | Audit-protokolliert
2026-06-03 | Alltagshilfe | Monatsbericht Lieferungs-Log | monthly_report_deliveries Tabelle + RLS + Unique-Index | Erledigt | 100% | supabase/migrations/20260603_000041_monthly_report_deliveries.sql | Audit-Trail
2026-06-03 | Alltagshilfe | Send-to-Management Aktion + E-Mail | PDF + CSV Anhang, Resend, idempotent, gateskey-Permission | Erledigt | 100% | src/app/actions/monthly-report.ts, src/lib/email/monthly-report.ts | Vorlagen DE/EN/TA
2026-06-03 | Alltagshilfe | Bericht-UI: Stunden je MA + Versand-Panel | Cross-Kunden Rollup + Status, Empfänger, nächster Lauf, Resend | Erledigt | 100% | src/app/(dashboard)/reports/alltagshilfe/page.tsx, src/components/reports/SendMonthlyReportButton.tsx | Pflegegrad-Pills inline
2026-06-03 | Berichte | ReportLibrary Karte für Monatsbericht | Herz-Icon-Karte + Alltagshilfe-Kategorie | Erledigt | 100% | src/components/reports/ReportLibrary.tsx | —
2026-06-03 | Branding | Logo-Komponente + brand-strings | Zentrale <Logo /> + <LogoMark /> mit 4 Größen, Filter-Invert | Erledigt | 100% | src/components/brand/Logo.tsx, src/components/brand/brand-strings.ts, public/priya-logo.png | weiße Wortmarke auf dunkel
2026-06-03 | Branding | Sidebar mit Logo + Toggle | Eingeklappt: Mini-Logo + Chevron · Ausgeklappt: groß + Chevron | Erledigt | 100% | src/components/layout/Sidebar.tsx, src/components/layout/AuthBrandPanel.tsx | Hydrierungs-Fix mit suppressHydrationWarning
2026-06-03 | Chat | Tipp-Indikator (Broadcast) | Supabase Realtime broadcast Kanal, throttled 2s + stop 3s | Erledigt | 100% | src/hooks/chat/useTyping.ts, src/components/chat/ChatThread.tsx | X tippt… / X und Y tippen…
2026-06-03 | Chat | Inline Shift/Visit Link-Karten | #shift-1234 / #visit-1234 Pattern → Pille mit Link zum Plan | Erledigt | 100% | src/components/chat/InlineLinkCard.tsx, MessageBubble.tsx | —
2026-06-03 | Benachrichtigungen | Bildschirm-Neuaufbau nach Prototyp | 4 KPI-Karten, Filter-Pillen, Datums-Buckets, farbige Icon-Kacheln, Fußnote | Erledigt | 100% | src/components/notifications/NotificationsPage.tsx | Heute/Gestern/Diese Woche gruppiert
2026-06-03 | Einstellungen | Bildschirm-Neuaufbau nach Prototyp | 2-Tier Nav, 8 Karten, Sticky-Side-Nav, nummerierte Sektion-IDs | Erledigt | 100% | src/components/settings/SettingsPage.tsx, src/lib/constants/routes.ts | Rollen-Matrix, Plan-Karte, Integrations-Grid
2026-06-03 | i18n | 2100 Schlüssel je Locale | Strikte Parität DE/EN/TA (von 1701 auf 2100 gewachsen) | Erledigt | 100% | messages/{de,en,ta}.json | keine fehlenden Keys
2026-06-04 | Rechnungen | Liste + Finanzen Politur | Farbstreifen auf KPI-Kacheln, Lexware-Sync-Knopf, Listen-Parität zum Prototyp | Demnächst | 25% | src/components/invoices/InvoicesPage.tsx | nächste Iteration
2026-06-04 | Kunden | Kunden-Liste Status-Dropdown | Status-Dropdown mit farbigen Punkten (Aktiv/Urlaub/Pausiert/Auslaufend/Inaktiv) | Demnächst | 10% | src/components/clients/ClientsPageClient.tsx | client_status enum erforderlich
2026-06-04 | Objekte | Liste Typ-Icons + 'Unzugewiesen' kursiv | Farbige Icon-Kacheln je Typ, italic Unzugewiesen, NEW-Pills | Demnächst | 10% | src/components/properties/PropertiesPageClient.tsx | —
2026-06-04 | Mitarbeiter | Mitarbeiter-Liste Wochenstunden + Urlaub | Stunden-Fortschrittsbalken, MED-CERT/NEW Pills, Urlaubssaldo N/30 | Demnächst | 10% | src/components/employees/EmployeesPageClient.tsx | —
2026-06-04 | Mobile | React Native App | Native Mobile-App pro Spec | Geplant | 0% | — | Tier 4
2026-06-04 | Betrieb | Hetzner Cloud (DE) + Backups | DSGVO-Hosting in DE, tägliche Backups, 30 Tage Aufbewahrung | Geplant | 0% | — | Migration aus Vercel
Gesamt |  |  | Erledigt

## Status (EN)
Implementation Status — Priya's Cleaning Service
Period: May 5, 2026 – June 3, 2026 · As of: June 4, 2026
Date | Module | Feature | Description | Status | Progress | Files | Notes
2026-05-05 | Audit | Requirements audit | Full assessment of 78 requirements from spec v1.0 | Done | 100% | AUDIT_REPORT.md | Tier 0/1/2/3/4 plan derived
2026-05-05 | Sicherheit | Self-role lock trigger | BEFORE-UPDATE trigger blocks self-promotion on profiles | Done | 100% | supabase/migrations/20260506_000024_lock_profile_self_role.sql | Idempotent, RLS-aligned
2026-05-05 | Schulungen | Inline training signatures | signature_svg column with 64 KB CHECK constraint | Done | 100% | supabase/migrations/20260506_000025_training_signature_inline.sql | Replaces storage round-trip
2026-05-05 | i18n | Auth pages translated | Login, register, onboarding flows DE/EN/TA active | Done | 100% | src/app/(auth)/**, messages/*.json | all strings out of hardcodes
2026-05-05 | Dashboard | Sidebar realtime counts | loadSidebarCounts() — real counts incl. unread chats | Done | 100% | src/lib/api/sidebar.ts | replaces mock defaults
2026-05-06 | Schulungen | Training realtime publication | Training tables added to supabase_realtime publication | Done | 100% | supabase/migrations/20260507_000026_training_realtime.sql | useTrainingRealtime hook wired
2026-05-06 | Mitarbeiter | Profiles→employees link | handle_new_user() inserts employees row + backfill | Done | 100% | supabase/migrations/20260507_000027_employees_from_profiles.sql | Fixes 0/3 visible employees
2026-05-06 | Mitarbeiter | Invite link trigger | Trigger links by email when invite is accepted | Done | 100% | supabase/migrations/20260507_000028_employee_invite_link.sql | placeholder→real profile
2026-05-06 | Mitarbeiter | Admin invite flow | createEmployeeAction uses supabase.auth.admin.inviteUserByEmail | Done | 100% | src/app/actions/employees.ts | inviteStatus returned
2026-05-06 | Mitarbeiter | Real role chips | chipFromProfileRole(role, hasMandatory) replaces mock | Done | 100% | src/lib/api/employees.ts | pm/field/trainee + outstanding mandatory training
2026-05-06 | Schulungen | Assignment picker fix | status='active' filter removed → 32 employees visible | Done | 100% | src/lib/api/training.ts | Status badges added
2026-05-06 | Benachrichtigungen | Push + in-app notifications | emitNotification on assign + WebPush fan-out | Done | 100% | src/lib/notifications/*.ts | VAPID keys required
2026-05-07 | Chat | Optimistic+realtime dedup | replace(tempId, real) in useMessages cache | Done | 100% | src/hooks/chat/useMessages.ts, useSendMessage.ts | fixes duplicate display
2026-05-07 | Chat | Video attachments | Video preview in composer + bubble | Done | 100% | src/components/chat/Composer.tsx, MessageBubble.tsx | new kind: video
2026-05-07 | Chat | Real avatars | computeInitials() with \p{L} Unicode + green DM tones | Done | 100% | src/components/chat/MessageBubble.tsx, ChatThread.tsx | no more '—'
2026-05-07 | i18n | Canonical format helpers | useFormat() hook + asAppLocale + formatDate/currency | Done | 100% | src/lib/utils/i18n-format.ts | replaces 15+ hardcodes
2026-05-07 | i18n | Locale sweep across components | 15+ components migrated to useFormat() | Done | 100% | src/components/** | no English date leak in DE
2026-05-07 | Dashboard | Real activity feed | loadDashboard joins profiles + RecentActivity translated | Done | 100% | src/lib/api/dashboard.ts, RecentActivity.tsx | mock actor removed
2026-05-07 | Dashboard | Team utilization real | TeamLoad.role from profiles, sorted by pct desc | Done | 100% | src/lib/api/dashboard.ts, TeamUtilization.tsx | employees.role.* translations
2026-05-08 | Berichte | PDF: satisfaction report | renderSatisfaction() for reports PDF | Done | 100% | src/lib/pdf/reports-pdf.ts | NPS + reviews
2026-05-08 | Berichte | PDF: open invoices | renderOpenInvoices() with days-overdue | Done | 100% | src/lib/pdf/reports-pdf.ts, src/app/api/reports/export/route.ts | loads real invoice list
2026-05-08 | Berichte | Alltagshilfe PDF | Multi-page renderer with addPage() per client | Done | 100% | src/lib/pdf/alltagshilfe-pdf.ts | health-insurance billing
2026-05-08 | API | CSV export endpoints | /api/clients, /api/invoices, /api/employees ?format=csv | Done | 100% | src/app/api/{clients,invoices,employees}/route.ts | csvEscape helper
2026-05-08 | Aufräumen | Dead buttons cleaned up | ClientDetail/InvoicesPage buttons disabled with tooltip | Done | 100% | src/components/clients/ClientDetail.tsx, InvoicesPage.tsx | coming-soon DE/EN/TA
2026-05-08 | Qualität | Final recheck | tsc, next lint, next build — 37/37 pages green | Done | 100% | — | 0 errors, 0 warnings
2026-05-08 | Tier 3 | REST API v1 + OpenAPI | /api/v1 with OpenAPI 3.0 spec | Planned | 0% | — | after stabilization
2026-05-08 | Tier 3 | Offline PWA cache | next-pwa for real offline mode | Planned | 0% | — | service worker
2026-05-08 | Tier 3 | Lexware auto-invoice cron | Monthly cron generates Lexware invoices | Planned | 0% | — | Twilio + Lexware creds
2026-05-08 | Betrieb | VAPID + backups + uptime | Prod config for push, backups, monitoring | In Progress | 25% | — | GitHub secrets pending
2026-05-12 | Tier 3 | REST API v1 + OpenAPI | Full /api/v1 surface with OpenAPI 3.0 spec + JSON endpoint | Done | 100% | src/app/api/v1/**, src/app/api/v1/openapi.json/route.ts | supersedes May-8 'Planned'
2026-05-12 | Security | API key management | API keys CRUD + hashed storage + UI at /settings/api-keys | Done | 100% | supabase/migrations/20260512_000029_api_keys.sql, src/app/actions/api-keys.ts | admin-only RBAC
2026-05-13 | Invoices | Invoice periods + §13b UStG | period_start/end fields + reverse-charge detection for EU B2B | Done | 100% | supabase/migrations/20260513_000030_invoice_period.sql | VAT-free automatic
2026-05-14 | Security | Sign-up role locked | Trigger forces 'employee' on self-signup | Done | 100% | supabase/migrations/20260514_000031_lock_signup_role.sql | blocks self-promo
2026-05-15 | Time tracking | Uniqueness check | One entry per (employee, shift) prevents double-clock | Done | 100% | supabase/migrations/20260515_000032_time_entries_unique.sql | —
2026-05-16 | Schedule | Shift exclusion constraint | GIST exclusion prevents overlapping shifts per employee | Done | 100% | supabase/migrations/20260516_000033_shift_exclusion.sql | —
2026-05-17 | Schedule | iCal token with expiry | Per-user token rotates; expiry for external calendars | Done | 100% | supabase/migrations/20260517_000034_ical_token_expiry.sql | —
2026-05-18 | Performance | Hot-path indexes | 10+ indexes for shifts, invoices, employee lists | Done | 100% | supabase/migrations/20260518_000035_perf_indexes.sql | measured 2-5× faster
2026-05-18 | Quality | React-doctor audit | 3 real bugs identified + fixed (stale state, shift orphan, PDF order) | Done | 100% | src/components/onboarding/OnboardVideos.tsx, DraftEditor.tsx | 21 false positives suppressed
2026-05-20 | Invoices | Complete invoice system schema | Assignments, Alltagshilfe budgets, invoice_payments, invoice_sequences | Done | 100% | supabase/migrations/20260520_000036_invoice_system.sql | Phase 1 of 2
2026-05-20 | Invoices | Exporter abstraction | InvoiceExporter interface + InternalExporter + LexwareExporter | Done | 100% | src/lib/invoicing/exporter/** | pluggable destinations
2026-05-20 | Everyday Help | AlltagshilfeBudgetCard | §45b SGB XI Entlastungsbetrag display + remainder calc | Done | 100% | src/components/invoices/AlltagshilfeBudgetCard.tsx | €1,575/yr cap
2026-05-21 | Invoices | Schema fixes phase 2 | Clients billing fields, shifts.billing_status, audit hooks | Done | 100% | supabase/migrations/20260521_000037_invoice_system_fixes.sql | —
2026-05-22 | Training | Training video bucket + upload | Supabase storage bucket + VideoUploadField component | Done | 100% | supabase/migrations/20260522_000038_training_videos_bucket.sql, src/components/training/VideoUploadField.tsx | captions pending
2026-06-01 | Master data | Intake spec fields | First/last name, address, Pflegegrad, cleaning rhythm, contract fields | Done | 100% | supabase/migrations/20260601_000039_intake_spec_fields.sql | DOB, Abtretung, mandatory-training RPC
2026-06-01 | Clients | Expanded intake forms | Stepper UI, sectioned cards, Pflegegrad selector, YesNoTile, side summary | Done | 100% | src/components/clients/CreateClientForm.tsx | GDPR footer, all 3 locales
2026-06-01 | Onboarding | Video gate for new staff | system_unlocked_at mandatory sequence before dashboard access | Done | 100% | src/app/(dashboard)/layout.tsx, src/components/onboarding/OnboardVideos.tsx | mandatory training
2026-06-02 | Lexware | Sync state + voucher dedup | lexware_sync_status enum, lexware_voucher_id unique index, attempts, last_error | Done | 100% | supabase/migrations/20260602_000040_lexware_reconciliation.sql | M1 reconciliation
2026-06-02 | Lexware | List paid vouchers | Lexware client extension: GET /vouchers?status=paid | Done | 100% | src/lib/lexware/client.ts | —
2026-06-02 | Lexware | Sync chip in list + detail | Coloured pill per invoice (queued/synced/failed) | Done | 100% | src/components/invoices/InvoicesPage.tsx, InvoiceDetail.tsx | —
2026-06-02 | Lexware | Nightly retry-sweep cron | retryLexwarePushSweep() runs daily + backoff | Done | 100% | src/app/api/jobs/lexware-retry/route.ts, src/lib/lexware/reconcile.ts | Vercel Hobby cron
2026-06-02 | Lexware | Payment sync from Lexware | pullLexwarePaymentsForAllOrgs() daily pull + reconciliation | Done | 100% | src/app/api/jobs/lexware-payments-sync/route.ts | —
2026-06-02 | Lexware | Manual retry + pull buttons | Server actions + UI in invoice detail | Done | 100% | src/app/actions/lexware-reconcile.ts | audit-logged
2026-06-03 | Everyday Help | Monthly report delivery log | monthly_report_deliveries table + RLS + unique index | Done | 100% | supabase/migrations/20260603_000041_monthly_report_deliveries.sql | audit trail
2026-06-03 | Everyday Help | Send-to-management action + email | PDF + CSV attached, Resend, idempotent, permission-gated | Done | 100% | src/app/actions/monthly-report.ts, src/lib/email/monthly-report.ts | templates DE/EN/TA
2026-06-03 | Everyday Help | Report UI: hours-per-staff + delivery | Cross-client rollup + status, recipient, next run, resend | Done | 100% | src/app/(dashboard)/reports/alltagshilfe/page.tsx, src/components/reports/SendMonthlyReportButton.tsx | care-level pills inline
2026-06-03 | Reports | ReportLibrary card for monthly report | Heart-icon card + Everyday Help category | Done | 100% | src/components/reports/ReportLibrary.tsx | —
2026-06-03 | Branding | Logo component + brand-strings | Central <Logo /> + <LogoMark /> with 4 sizes, filter-invert | Done | 100% | src/components/brand/Logo.tsx, src/components/brand/brand-strings.ts, public/priya-logo.png | white wordmark on dark
2026-06-03 | Branding | Sidebar with logo + toggle | Collapsed: mini-logo + chevron · Expanded: large + chevron | Done | 100% | src/components/layout/Sidebar.tsx, src/components/layout/AuthBrandPanel.tsx | hydration fix with suppressHydrationWarning
2026-06-03 | Chat | Typing indicator (broadcast) | Supabase Realtime broadcast channel, throttled 2s + stop 3s | Done | 100% | src/hooks/chat/useTyping.ts, src/components/chat/ChatThread.tsx | X is typing… / X and Y…
2026-06-03 | Chat | Inline shift/visit link cards | #shift-1234 / #visit-1234 pattern → pill linking to schedule | Done | 100% | src/components/chat/InlineLinkCard.tsx, MessageBubble.tsx | —
2026-06-03 | Notifications | Screen rebuild to prototype | 4 KPI cards, filter pills, date buckets, coloured icon tiles, footer note | Done | 100% | src/components/notifications/NotificationsPage.tsx | Today/Yesterday/Week grouped
2026-06-03 | Settings | Screen rebuild to prototype | 2-tier nav, 8 cards, sticky side nav, numbered section IDs | Done | 100% | src/components/settings/SettingsPage.tsx, src/lib/constants/routes.ts | role matrix, plan card, integrations grid
2026-06-03 | i18n | 2100 keys per locale | Strict parity DE/EN/TA (grew from 1701 to 2100) | Done | 100% | messages/{de,en,ta}.json | no missing keys
2026-06-04 | Invoices | List + Finances polish | Colour stripes on KPI tiles, Lexware-Sync button, list parity with prototype | Coming soon | 25% | src/components/invoices/InvoicesPage.tsx | next iteration
2026-06-04 | Clients | Customer list status dropdown | Status dropdown with coloured dots (Active/Vacation/Paused/Ending/Inactive) | Coming soon | 10% | src/components/clients/ClientsPageClient.tsx | needs client_status enum
2026-06-04 | Properties | List type icons + 'Unassigned' italic | Type-coloured icon tiles, italic Unassigned, NEW pills | Coming soon | 10% | src/components/properties/PropertiesPageClient.tsx | —
2026-06-04 | Employees | Employees list weekly hours + vacation | Hours progress bar, MED-CERT/NEW pills, vacation balance N/30 | Coming soon | 10% | src/components/employees/EmployeesPageClient.tsx | —
2026-06-04 | Mobile | React Native app | Native mobile app per spec | Planned | 0% | — | Tier 4
2026-06-04 | Operations | Hetzner Cloud (DE) + backups | GDPR hosting in DE, daily backups, 30-day retention | Planned | 0% | — | migration from Vercel
Total |  |  | Done